## About
How to Use This Template
Time Entry
Step 1: | Enter the Year
Step 2: | Choose the Start Day
|  |  | Year | 2026
Step 3: | Customize the Theme Colors / Fonts
| Go to Page Layout > Themes to choose different colors and fonts. |  | Start Day of Week | 1
Step 4: | Print to Paper or PDF
Print the entire workbook, or print only the selected worksheets.

## September
2026-09-01
2026-08-30 |  | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 |  | 2026-09-04 | [6 empty] | 2026-09-05
2026-08-30 |  | 2026-08-31 | 2026-09-01 | 2026-09-02 | 2026-09-03 |  | 2026-09-04 | [6 empty] | 2026-09-05
2026-09-06
|  | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 |  | 2026-09-11 | [6 empty] | 2026-09-12
REII: Individual checkpoint due - nRF24 link characterisation report + recommended config
2026-09-13
|  | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 |  | 2026-09-18 | [6 empty] | 2026-09-19
REII: I3 begins - ICD_REII drafted & signed off in week 1
2026-09-20
|  | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 |  | 2026-09-25 | [6 empty] | 2026-09-26
2026-09-27
|  | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 |  | 2026-10-02 | [6 empty] | 2026-10-03
MCTR1: Design of carriage v2 |  |  |  | MCTR1: ICD templates, carriage build
2026-10-04
|  | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 |  | 2026-10-09 | [6 empty] | 2026-10-10
Notes | [6 empty] | 2026-08-01 | [7 empty] | 2026-10-01
[7 empty] | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S
Shared milestone calendar sodat ons kan sien wanneer wie wat gedoen wil he, en sodat ons n volle prentjie het | [12 empty] | 2026-08-01 | [5 empty] | 2026-10-01 | 2026-10-02 | 2026-10-03
van die tyd wat oor is en wat verby gaan. | [6 empty] | 2026-08-02 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 |  | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10
[7 empty] | 2026-08-09 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 |  | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17
Sit asseblief julle eie milestones in onder jou package naam | [6 empty] | 2026-08-16 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 |  | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24
[7 empty] | 2026-08-23 | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 |  | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31
[7 empty] | 2026-08-30 | 2026-08-31
| Time to DEMO: |  | 4 | weeks | and | 5 | 2026-08-27: days

## October
2026-10-01
2026-09-27 |  | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 |  | 2026-10-02 | [6 empty] | 2026-10-03
2026-09-27 |  | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 |  | 2026-10-02 | [6 empty] | 2026-10-03
MCTR1: carriage v2 test
2026-10-04
|  | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 |  | 2026-10-09 | [6 empty] | 2026-10-10
|  | MCTR1: Carraige v2 design | MCTR1: Gearbox design | MCTR2: Motor characterise in heavy current lab with avalable VFD's | MCTR1: Carriage v2 build EEII2: Contact suppliers for material quotes, Femm simulation tests, Speak to Hopewell on campus Obtain winding wire |  | MCTR1: Carriage motor drive test, carriage v3 test EEII1:Order heat sinks and power supply(at the latest) MCTR2: Starting with all final draft printing parts REII: controller board delivery (estimate, Checkpoint2) - input to ESP32 nRF stub + integration
2026-10-11
|  | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 |  | 2026-10-16 | [6 empty] | 2026-10-17
REII: gate - Controller Spec + ESP32 codebase obtained; board powered (planned, not agreed) |  | EERI321: PRACTICAL 2 submission | MCTR2: Start with gearbox casing build EEII2: Required voltage calculations, Switching circuit prelim | REII: ICD Sec 4 payload freeze w/ MCTR+EEII (planned, not agreed) · D-01 byte maps + version byte rule | EERI321: Semester T3 |  | MCTR1: Enclosure v1 test, ICD complete with- REII, ICD complete with- MCTR2? REII: ESP32 nRF24 stub complete - RX mode + Table 2 SPI read-back (planned, not agreed) | [6 empty] | EEII1: ICD complete with REII and MCTR2
2026-10-18
|  | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 |  | 2026-10-23 | [6 empty] | 2026-10-24
EEII1:Working low voltage switching circuit in thevinin lab(one IGBT +driver +opto) |  | REII: STM32F411 dongle bring-up (planned, not agreed) · CDC echo capture · SPI + Table 2 radio init read-back · USB<->RF bridge PING/PONG | REII: dashboard cmd + telemetry path (planned, not agreed) · Idle/Move/E-stop/Magnet cmd exec · telemetry no sequence gaps · fault display capture (internal target) | EEII1: PCB manufactured by MR van Huysteen | REII: bench for 26 Oct (planned, not agreed) · PING->PONG ch77/2M, 200-pkt smoke CSV · 32-B pack/unpack byte-exact loopback · else raise NCRs before group test |  | MCTR1: Enclosure final + fit test | [6 empty] | EEII1: Final Drive circuit complete+DB box wired
2026-10-25
|  | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 |  | 2026-10-30 | [6 empty] | 2026-10-31
REII: pre-integration (planned, not agreed) · isolation bench-verify + HW E-stop path (pre-live drivers) · MCTR-I profile format D-04 + encoder handoff |  | Group: First integration test EEII1: Testing with PWM of REII in Heavy current lab REII: dashboard + dongle + controller link | REII: participation evidence captured - scope TBD, confirm w/ lecturer (F-08) | REII: anti-sway model + open-loop profile generator (planned, not agreed) · pendulum model; sway freq identified · else S-curve baseline only (D-04) | EERI 324 |  | REII: on-rail integration - INTERFACE_MATRIX rows (planned, not agreed) · rail RF re-survey + group channel plan · 5/10 m N=1000 ACK runs + NLOS point · evidence: results/i3_rail/ + TEST_LOG
2026-11-01
|  | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 |  | 2026-11-06 | [6 empty] | 2026-11-07
Notes | [6 empty] | 2026-09-01 | [7 empty] | 2026-11-01
[7 empty] | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S
[9 empty] | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 |  | 2026-11-01 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07
[7 empty] | 2026-09-06 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 |  | 2026-11-08 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14
[7 empty] | 2026-09-13 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 |  | 2026-11-15 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21
[7 empty] | 2026-09-20 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 |  | 2026-11-22 | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28
[7 empty] | 2026-09-20: 2026-09-27; 2026-09-21: 2026-09-28; 2026-09-22: 2026-09-29; 2026-09-23: 2026-09-30 |  | 2026-11-29 | 2026-11-30
| Time to DEMO: |  | 4 | weeks | and | 5 | 2026-09-24: days

## November
2026-11-01
2026-11-01 |  | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 |  | 2026-11-06 | [6 empty] | 2026-11-07
2026-11-01 |  | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 |  | 2026-11-06 | [6 empty] | 2026-11-07
|  | EERI 321 |  | REII: rail sway measurement (planned, not agreed) · flat vs shaped profile · log + plot position/time · pass bound = internal, not SysRS | REII: obstacle/path-planning gate (planned, not agreed) · known-obstacle map source cited · planner output = MCTR cmd format · run vs modelled path evidence |  | EERI 325 Group: Integration successful REII: REII integration verified gate (link + dashboard + sway) · INTERFACE_MATRIX all-pass or NCRs w/ owners
2026-11-08
|  | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 |  | 2026-11-13 | [6 empty] | 2026-11-14
|  | EEII 321 Group: Finalize all ICDs REII: ICD_REII signed (v1.0, v1.1 if pins/timings changed) | REII: I3 handoff pack + demo evidence (planned, not agreed) · INTERFACE_MATRIX + TEST_LOG filled · NCR list w/ owners + sign-off · demo run-through capture | Group: Finish performance test reports and Individual portfolios REII: RF/rail test report + individual portfolio | Group: Final touches REII: demo dry-run + evidence pack check (planned, not agreed) |  | DEMO
2026-11-15
|  | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 |  | 2026-11-20 | [6 empty] | 2026-11-21
Presentation + Portfolio Due
2026-11-22
|  | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 |  | 2026-11-27 | [6 empty] | 2026-11-28
2026-11-29
|  | 2026-11-30 | 2026-12-01 | 2026-12-02 | 2026-12-03 |  | 2026-12-04 | [6 empty] | 2026-12-05
2026-12-06
|  | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 |  | 2026-12-11 | [6 empty] | 2026-12-12
Notes | [6 empty] | 2026-10-01 | [7 empty] | 2026-12-01
[7 empty] | S | M | T | W | T | F | S |  | S | M | T | W | T | F | S
[11 empty] | 2026-10-01 | 2026-10-02 | 2026-10-03 |  |  |  | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05
[7 empty] | 2026-10-04 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 |  | 2026-12-06 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12
[7 empty] | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 |  | 2026-12-13 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19
[7 empty] | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 |  | 2026-12-20 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26
[7 empty] | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 |  | 2026-12-27 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31
| Time to DEMO: |  | 4 | weeks | and | 5 | 2026-10-29: days