## Detail Time Estimate
EngDes26 | REII TimeSheet
Updated 29 Oct 2026: rows from 24 Oct replaced with actual work (real minutes to fill in) and the plan to 16 Nov
Group Number: |  | 13
Student Name: |  | Riekert Nel
Student Number: |  | 40496325
Date | Assignment Task | Task start | Task completed when | Time estimate (in min) | Concerns or comments (in words) | Real Time (in min)
2026-09-03 | Preparation | Obtain specification, SoW pack and report template | Report structure set up; Group 13 roles confirmed | 90 | Split the reading with my partner and compared notes afterwards so we both worked from the same requirement set. (45 min each) | 110
2026-09-03 | Preparation | Set up folder structure and risk-register template | Repo layout and meeting-notes folder created | 60 | Started the risk register from a blank template - only the categories were drafted on day one. (split task) | 75
2026-09-04 | Requirements analysis | Study EngDes26 SysRS v1.0 and the REII SoW | REII-relevant clauses highlighted (FR12, FR13, PHY2/3, DR4/DR5) | 180 | SysRS is Rev 0 'for discussion' with Sec 5.1 verification methods deferred - logged that as an open item instead of assuming values. | 200
2026-09-04 | RF Characterisation - plan | Set up PlatformIO test firmware; check both nRF24L01 boards | Firmware built and flashed; live link proved on dev boards | 150 | The checkpoint task needs a live link first; both boards came up on the control channel. | 170
2026-09-05 | Requirements analysis | Apply the course requirement-parsing template | First 7 candidate REII requirements drafted | 120 | Used the actor-condition-shall-action-object-constraint template from the course notes; wording still to be reviewed with the team. | 135
2026-09-05 | RF Characterisation - execute | Distance sweep 1-190 m, ACK and NOACK, both rates | CSVs saved under rf_characterisation/results/ | 300 | NOACK PER degrades badly at 190 m (1 Mbps 80.00 %, 2 Mbps 38.10 %) - captured as a risk rather than glossed over. | 330
2026-09-06 | Risk analysis | Draft initial risk register (technical, interface, schedule, safety) | Risk register v0.1: 16 risks with owners | 120 | Includes the unsigned ICD, controller-board delivery date, rail access and far-end link margin. | 140
2026-09-06 | Context diagram | Draft the system context diagram in Draw.io | SCD v0.1: operator, dashboard, dongle, controller, crane | 150 | System-of-Interest boundary kept at PC dashboard + NodeMCU-32S (ESP32) USB ground-station dongle per the ICD. | 165
2026-09-06 | RF Characterisation - execute | Interference benchmark and channel survey | Channel occupancy captured; candidate channels shortlisted | 180 | Campus Wi-Fi occupancy checked; candidate set [4, 50, 73, 77, 81] kept 4 or more channels apart (proposal only). | 200
2026-09-07 | Meeting - team | Team meeting: requirement ownership and checkpoint split | Actions recorded in meeting notes | 60 | Agreed who drafts which section; RF report before architecture. Both attended, actions dated. | 90
2026-09-07 | System Architecture Design | Draft system architecture model (F/U 6.0 Remote Controller) | 6.1-6.5 decomposition laid out | 180 | Dashboard application, dongle MCU, nRF24L01 module, antenna and USB power split as separate units; kept consistent with the SCD. | 195
2026-09-08 | FFBD Development | Start system FFBD - top-level function flow | Connect - command - telemetry chain drafted | 150 | Following the P2 slide style; numbering chosen so functions can later be traced to requirements. | 170
2026-09-08 | RF Characterisation - execute | Repeatability spot-checks and best-channel decision data | Rate/mode comparison table drafted | 150 | Every distance/rate point is a single burst (n = 1) - recorded as a limitation for the report. | 300
2026-09-09 | FFBD Development | Decompose REII branches 3.2 / 3.3 / 3.5 | REII sub-functions drafted and numbered | 180 | 3.2 link setup, 3.3 operator-command path, 3.5 telemetry path; handshake wording left open pending the ICD discussion. | 200
2026-09-09 | RF Characterisation - report | Start RF report: method, setup, Tables 1-2 | Sections 1-3 drafted | 180 | Setup photos and table values taken straight from the CSVs - no number typed from memory. | 150
2026-09-10 | RF Characterisation - report | Figures: PER vs distance, channel-survey plots | Figure list and captions drafted | 150 | Plots regenerated from the raw CSVs so the figures match the data exactly. | 120
2026-09-10 | Meeting - team | Team review of the RF report draft | Comments merged into the report | 60 | Partner flagged two unclear table captions; fixed before the final polish pass. | 65
2026-09-10 | RF Configuration | Fill the recommended configuration (channel, rate, PA, ARC/ARD) | Recommended config drafted: ch 77, 2 Mbps, PA_MAX, ARC 5, ARD 500 us | 90 | ARC 5 (ICD) vs ARC 15 (test firmware) conflict noted as an open item instead of silently picking one. | 30
2026-09-11 | RF Characterisation - report | Polish report, check figures, export final PDF | Individual checkpoint submission uploaded | 180 | Checkpoint due today (11 Sep); final read-through for captions and references. | 120
2026-09-11 | Documentation | Post-submission checkpoint notes and questions | Follow-up question list prepared | 45 | Wrote down follow-ups (verification methods, PT3 threshold) instead of guessing the values. | 50
2026-09-14 | ICD Drafting | Read ICD template; draft Sec 1 (physical) and Sec 2 (data-link) | Sec 1-2 drafted from the measured RF configuration | 210 | I3 begins this week - ICD drafted in week 1. Table 2 values taken from our own measured configuration. | 230
2026-09-14 | Meeting - team | I3 kick-off: ICD ownership and signature plan | Owner and sign-off route agreed | 60 | Agreed to draft first, then hold the payload workshop with MCTR/EEII before any signature. | 70
2026-09-15 | ICD Drafting | Draft Sec 3 application-layer direction | Sec 3 direction text written; Sec 4 left TBD | 150 | Sec 4 (32-byte maps) deliberately left TBD - no invented application byte maps. | 165
2026-09-15 | Requirements analysis | Cross-check requirements against SoW scope | REII scope items 1-6 mapped to requirements | 120 | Kept SoW scope separate from SysRS requirements; where they differ, the difference was noted rather than merged. | 130
2026-09-16 | Meeting - team | Team meeting: reliability model and the ARC conflict | Decision note drafted; conflict logged | 75 | FFBD 'handshake' vs ICD 'no software ARQ' discussed; interpretation recorded as open item V-02 for the controller owner. | 85
2026-09-16 | FFBD Development | Review FFBD against the ICD draft wording | Reconciliation notes written | 90 | Did not edit either artefact - conflicts listed so they can be resolved at the ICD freeze. | 100
2026-09-17 | Contradictions / assumptions | Log contradictions (legacy numbers, 50 ms internal target) | Contradiction register updated in the progress record | 120 | Legacy requirement numbers vs SysRS clause numbers recorded as a conflict to report, not to resolve quietly. | 135
2026-09-17 | Application Protocol Design | Collect protocol constraints and open questions | Q1-Q15 open-question list drafted | 150 | Constraints sourced from the ICD, RF configuration and SysRS only; anything unsourced marked TBD. | 165
2026-09-18 | Meeting - team | I3 week-1 wrap-up: decisions D-00a/b recorded | Decision-log entries written with dates and owners | 60 | Agreed to record every decision with date, owner and evidence; D-01 left open pending the payload workshop. | 70
2026-09-18 | Documentation | Update progress and milestone record | Statuses re-checked against repository evidence | 60 | Only the RF campaign carries measured evidence; everything else kept at its honest status. | 75
2026-09-21 | Application Protocol Design | Draft protocol proposal: requirement-to-field mapping | Proposal Sec 1-5 written | 240 | Each field traced back to a requirement; no field added without a source. | 260
2026-09-22 | Application Protocol Design | Define alternatives and weighted criteria | 9 alternative pairs; criteria C1-C9 defined | 210 | Criteria weighted before scoring so the trade study was not fitted to a preferred answer. | 230
2026-09-23 | Application Protocol Design | Run the trade study; draft the candidate downlink map | Scoring complete; Sec 6-10 drafted | 240 | Marginal scores flagged where criteria nearly tie; the downlink map is still PROPOSED, not agreed. | 260
2026-09-24 | Application Protocol Design | Draft uplink map, enum tables and the 32-byte arithmetic proof | Sec 11-12 and Sec 18 complete; byte count checked | 210 | Kept the 32-byte constraint explicit - proved both maps fit before presenting them. | 230
2026-09-24 | Meeting - team | Team review of the application-protocol proposal | Review comments captured and applied | 60 | Partner checked the field list against FR12/FR13; two telemetry fields re-worded. | 70
2026-09-25 | Application Protocol Design | Complete proposal Sec 13-20 (validation, safety, proposed ICD Sec 4) | Proposal document complete (status: PROPOSAL only) | 270 | Reliability section separates L1-L6 so the FFBD/ICD clash is addressed without adding an application-level ARQ. | 290
2026-09-28 | Risk analysis | Re-score risks after the protocol and ICD work | Risk register v0.2 with mitigations and owners | 120 | Added 'late Sec 4 freeze invalidates firmware' and 'component scales wrong by a factor' risks. | 135
2026-09-29 | Documentation | Confirm the source-authority hierarchy | Authority notes corrected in the rules and source files | 90 | SysRS = requirements authority; SoW = own scope; ICD = interface authority only once signed. | 105
2026-09-30 | I3 Planning | Review the I3 planning pack (week plan, actions, decision log) | Open items D-01..D-06 and F-01..F-09 listed | 150 | Nothing marked done without evidence; empty TEST_LOG measurement rows were left empty. | 165
2026-09-30 | Meeting - team | Team meeting: what we need from MCTR and EEII | Ask-list drafted for the other packages | 60 | Payload-workshop prerequisites and the controller-spec request written down for the group chat. | 70
2026-10-01 | I3 Planning | Draft interface-matrix rows and evidence paths | Matrix rows drafted with CSV/log targets | 150 | Rows aligned to 5/10 m LOS, an NLOS point and the RF survey; blank rows are not passes - NCRs needed on failure. | 165
2026-10-02 | Safety / validation | Note the PHY2 hardware e-stop vs dashboard e-stop distinction | Safety-boundary note added to the validation record | 90 | The dashboard e-stop flag must not be presented as the hardware safety stop. | 105
2026-10-02 | Meeting - team | Meeting: participation evidence and rail access | Questions prepared for the lecturer (F-08) | 45 | No rail dates exist in the repository - the booking must be made explicitly; flagged as an action. | 55
2026-10-03 | Dashboard Requirements | Extract FR12/FR13 into dashboard requirement notes | Telemetry and command lists drafted | 120 | Internal 50 ms fault-display target recorded as an internal target, not as a SysRS requirement. | 135
2026-10-04 | I3 Planning | Review week plan weeks 7-10 against the real calendar | Week plan checked; dependencies listed | 90 | Board delivery (9 Oct estimate) and the unknown rail slot pulled out as blockers. | 100
2026-10-05 | Project Planning | Add REII entries to the shared group milestone calendar | 17 dated REII entries written to Group_milestones.xlsx | 150 | Gates labelled 'planned, not agreed' - the dates are ours to propose, not course-agreed. | 165
2026-10-05 | Documentation | Restructure the project dashboard README | Gist, status board, decisions and open questions rebuilt | 180 | Status board mirrored from the progress file so the two records do not drift apart. | 200
2026-10-08 | Application Protocol Design | Prepare the R12-R16 approval list and circulation note | Circulation message ready for the other packages | 90 | Questions phrased so the answers can be dropped straight into the decision log. | 105
2026-10-09 | Meeting - team | Group 13 meeting: ICD-001 scope, report & integration targets | Agreed Group 13 ICD-001 outline and subsystem interface owners | 60 | Confirmed Group 13 work package allocations (REII, MCTR 1, MCTR 2, EEII 1, EEII 2) and set 23 Oct as the ICD-001 Rev A release date. | 65
2026-10-09 | Integration Planning | List pre-integration test prerequisites (Sec 4.1 & Sec 4.2) | 4-stage REII integration checklist drafted (IF-E1.0 to FU8) | 120 | Defined the step-by-step verification stages: (1) USB link IF-E1.0, (2) 2.4 GHz air link IF10.0, (3) Header J1/J3.3 SPI & CE, and (4) full group signal handshake. | 130
2026-10-09 | Documentation | Review open interface questions across MCTR 1/2 and EEII 1/2 | Cross-package interface question list finalised | 60 | Clarified encoder 5 V to 3.3 V level shifting (MCTR 1), 24-bit ADC channels (MCTR 2 / EEII 1 / EEII 2), and optical isolation on VFD PWM lines. | 65
2026-10-09 | Report Writing Plan | Draft Group 13 report & ICD-001 section ownership | Outline circulated; Section 2.5, 3.5, 4 & 5.5 assigned | 90 | Target submission 23 Oct (ICD-001 Rev A); assigned IF1.0, IF6.0, IF10.0, Section 3.5 design decisions, Section 4 test plans, and Section 5.5 progress. | 95
2026-10-09 | Integration Planning | Map October milestone gates to day-by-day actions (9-23 Oct) | Action list built for ESP32-S3 & NodeMCU-32S bring-up | 60 | Aligned REII milestones (schematic check, dual-node firmware, 200-packet smoke test, and ICD-001 report) to the 23 Oct submission date. | 65
2026-10-09 | Hardware Bring-Up | Receive shared ESP32-S3 carrier board (FU8) & 5-sheet schematic | Board powered; 5-sheet schematic stored and inspected | 180 | Selected NodeMCU-32S (ESP32) for the USB ground station instead of Arduino Nano because 115 mA nRF24L01+ TX bursts caused Nano 3.3 V brownouts. | 195
2026-10-10 | Main Board Pin Map | Audit all 5 sheets of ESP32-S3 carrier schematic (Headers J1-J9) | Complete J1-J9 pin allocation table locked for all 5 packages | 150 | Reserved Header J7 for hardware timers (EEII 1 SPWM J7.6-J7.8, EEII 2 PWM J7.5, MCTR 1 PWM J7.9 & encoder J7.12); placed ON/OFF logic on J3/J4, analog on J6, and REII SPI on J1 + CE on J3.3. | 165
2026-10-11 | ESP32-S3 Crane Firmware | Scaffold ESP32-S3 crane firmware (SPI on J1, CE on J3.3, ADS1220) | Project builds in ESP-IDF; 4 MHz SPI & nRF24 PRX init ready | 180 | Capped Header J1 SPI clock at 4 MHz for clean signal edges on <= 150 mm jumpers and ensured CS lines stay mutually exclusive across radio, ADC, and SD. | 190
2026-10-12 | ICD Drafting | Prepare 32-byte fixed-point payload workshop options for Group 13 | Downlink (0xA5) and Uplink (0x81) byte-map options circulated | 120 | Used whole-number scaling (mm for position, mm/s for speed, kg x 10 for load cell, A x 10 for VFD and magnet current) to avoid floating-point rounding. | 130
2026-10-13 | Meeting - cross-package | Group 13 interface & 32-byte payload workshop (MCTR 1/2, EEII 1/2) | All subsystem pins and 32-byte telemetry fields agreed | 120 | Locked MCTR 1 PWM/dir/encoder (IF1.0), EEII 1 3-phase SPWM & current (IF6.0), EEII 2 magnet PWM & Byte 14 coil current (J6.8), and MCTR 2 load cell & brake (J4.8). | 135
2026-10-14 | ICD Drafting | Freeze IF10.0 32-byte Downlink (0xA5) & Uplink ACK (0x81) maps | IF10.0 specification, pinout and payload tables completed | 240 | Completed full IF10.0 ICD tables including 8-bit fault_flags (Byte 17) and system_health (Byte 18) plus MCU-side specifications for IF1.0 and IF6.0. | 255
2026-10-14 | Documentation | Update Group 13 interface inventory (Table 6) and functional units | FU1-FU11 and IF1.0-IF15.0 mapped in System Block Diagram | 60 | Synchronized Table 5 (Functional Units) and Table 6 (Interface Inventory) with Figure 1 System Block Diagram across all five disciplines. | 70
2026-10-15 | Ground-Station Bring-Up | NodeMCU-32S ground station (COM10): USB-CDC echo & decoupling | 10 uF + 100 nF caps soldered; USB serial CLI (ECHO/INFO) verified | 240 | Soldered 10 uF electrolytic + 100 nF ceramic decoupling capacitors directly across nRF Pins 1 & 2 on both radios; verified 115 200 bit/s USB serial link. | 250
2026-10-16 | RF Bench Verification | Execute TEST-REII-01 & TEST-REII-03: 200-packet live smoke test | Run 20261016_125349 logged (smoke.csv, groundstation.log, rig.log) | 300 | Verified isPVariant=1 and app_ch=77 (2477 MHz, 2 Mbps, ARC=5, ARD=500 us). Achieved 200/200 rig RX (PING #5-#204), 192/200 Auto-ACKs (4.0% PER), and 0.89 ms avg RTT (2.0 ms max) with concurrent ADS1220 & AHT20 polling. | 320
2026-10-17 | RF Bench Verification | Audit Run 20261016_125349 logs & close-range PA_MAX LNA behaviour | Confirmed 8 return-ACK drops were close-range (<1 m) PA_MAX saturation | 210 | Cross-checked smoke.csv timeouts (#18, #96, #97, #130, #152, #160, #190, #200) against rig.log: all 200 forward PINGs arrived; documented PA_LOW rule for <2 m bench tests. | 225
2026-10-18 | Application Protocol Code | Implement 32-byte command (0xA5) & ACK-payload (0x81) serialization | Fixed-point pack/unpack and static_assert(sizeof == 32) verified | 150 | Included EEII 2 magnet coil current on Byte 14 (0.1 A scale on pin J6.8), sequence counter duplicate filtering, and CRC-16 + magic-byte validation. | 160
2026-10-19 | Anti-Sway & Path Planning | Implement rope-length-aware smooth anti-sway speed ramp generator | Open-loop acceleration/deceleration ramp calculator completed | 240 | Designed self-ending velocity ramps on the PC dashboard so wireless jitter cannot destabilize load swing and lost-link timeouts stop motion safely. | 255
2026-10-20 | PC Operator Dashboard | Build Python PC control dashboard (controls, live telemetry & faults) | Dashboard GUI connected to NodeMCU-32S USB serial bridge | 300 | Implemented trolley/hoist/magnet controls, live sensor readouts (mm, mm/s, kg, A), simultaneous 8-bit fault checklist alerts, and software stop flag. | 315
2026-10-21 | Report Writing | Draft Group 13 Report & ICD-001 (Sections 2.5, 2.6, 3.5, 4 & 5.5) | REII ICD tables, design decisions, and integration plans merged into v7 | 360 | Compiled detailed pin/signal definitions for IF1.0, IF6.0, and IF10.0, Section 2.6 acceptance table (TEST-REII-01..04), and Section 3.5/4.1-4.3 text. | 300
2026-10-22 | Report Writing | Expand Section 5.5 progress with Milestone 4 smoke.csv plot & logs | 3-page Section 5.5 DOCX & Figure 5.5-2 generated from smoke.csv | 240 | Plotted per-round RTT, ACK distribution, and cumulative delivery from Run 20261016_125349; referenced groundstation.log and rig.log and prepared Figure 5.5-1 photo box. | 255
2026-10-23 | Report Finalisation | Insert bench setup photo (Fig 5.5-1); final review & submit ICD-001 Rev A | Group 13 Engineering Design Report (ICD-001 Rev A) finalised | 180 | Inserted MCU & ground-station bench photograph into Section 5.5, verified all Table of Contents/Figures/Tables numbering, and exported final Group 13 PDF. | 190
2026-10-23 | Pre-Integration Testing | Unpowered FU8 pin & 32-byte payload handshake check (Sec 4.2 Stage 4) | Bench verification of dashboard commands to J3, J4 & J7 headers | 180 | Verified with high-voltage power off that 32-byte packets toggle MCTR 1 (J7.9, J4.4-J4.5), EEII 1 (J7.6-J7.8, J3.4), MCTR 2 brake (J4.8), and EEII 2 magnet (J7.5, J3.6). | 178
2026-10-24 | Pre-Integration Testing | Flash Increment 3 ground station + crane firmware; run the dashboard end to end | Dashboard connects and shows PING hex, but no ACKs; crane logs 0 frames | 180 | Fault reproduced and logged (REII Progress/Latest Flashing Results ... .txt). Real minutes: fill in.
2026-10-27 | Debugging - RF link | Move nRF CE to J3.3 (MCP23017 GPA0) per ICD Table 31 in the NEWEST firmware; re-test | NEWEST firmware flashed on crane, GS and dashboard; link still dead | 240 | Found a payload-mode mismatch: crane static 32 B vs GS dynamic + ACK payload. Real minutes: fill in.
2026-10-28 | Debugging - RF link | Isolate the dead link: register dumps, CE/PRIM_RX sequencing, carrier + RPD tests, 126-channel scans | Crane registers correct but crane receiver deaf; crane module hears normally on the NodeMCU, so the fault is on the crane-board side | 300 | Cause: the MISO lead had been removed instead of the unused IRQ lead; fixed by a full rewire to the MCU wiring and header pinout document. Real minutes: fill in.
2026-10-28 | Increment 4 Rebuild | Rebuild crane (starter project), ground station (Increment 2) and smoke-test tool with automatic RF diagnosis | Smoke PASS with CE on J3.3: 200/200, 0.0 % PER, 0.84 ms max RTT, 200/200 telemetry (run 20261028_230328) | 300 | Increment 4/crane_rig_IDF v4.4.1, groundstation_PIO v4.1.0, tools/smoke_test.py. Real minutes: fill in.
2026-10-28 | Load Cell IF13.0 | Read the S-type load cell on J6 with the on-board ADS1220 (gain 128, ratiometric), tare + calibration | Real kg x 10 in Table 34 bytes 10-11; overload > 20 kg fault | 150 | HX711 not needed - ICD Table 38 primary path used. Real minutes: fill in.
2026-10-28 | PC Operator Dashboard | Dashboard v4: live load + USB cross-check, Tare / Calibrate, PA and clean-channel switching | Sessions 20261028_220935 and 20261029_000031 logged; channel 77 -> 80 -> 77 confirmed | 180 | Per-command telemetry.csv + events.log captured as FR12/FR13 evidence. Real minutes: fill in.
2026-10-29 | Documentation | Redo progress + milestones, timesheet, Increment 4 README and dashboard README; lock decisions from ICD-001 Rev A | Decisions D1-D19 locked; plan to 16 Nov written | 180 | Open questions in older markdown files closed by ICD-based decisions.
2026-10-30 | Crane MCU - IF1.0 (MCTR 1) | LEDC PWM on J7.9, IN1-IN4 on J4.4-J4.7 (one HW-095 for both motors), PCNT encoder on J7.12 | Motor runs both ways from the dashboard; counts per wheel turn measured; real trolley_pos / trolley_vel | 300 | PLANNED. MCTR 1 (29 Oct): 60 mm wheel, encoder on motor shaft. LEDs/scope first; their driver after their motor test (2 Nov). Gear ratio vs ICD settled by counting 10 wheel turns.
2026-10-31 | Crane MCU - IF15.0 + IF12.0 | Hoist brake J4.8 timing; magnet PWM J7.5 (20 kHz, 8.33 %) + J3.6 logic | Brake follows hoist command (release 50 ms before motion); magnet PWM measured on scope | 300 | PLANNED. Needs MCTR 2 brake module and EEII 2 switch module.
2026-11-01 | Crane MCU - ADC + safety | Share the ADS1220: load cell + magnet current (AN3); safe-hold state machine | Unplug GS -> speeds 0, brake clamps, magnet stays on; load cell still >= 20 Hz | 300 | PLANNED. Decision D10 (ADC schedule), D8 (500 ms lost link). VFD current is digital per EEII 1 (29 Oct), not on AN2.
2026-11-02 | Crane MCU - IF6.0 (EEII 1) | 3-phase SPWM on J7.6-J7.8, DRV_EN J3.4 (HIGH = enable), DRV_FAULT J3.5, 10 A overcurrent stop, hoist position estimate | Phases 120 deg apart on the scope before any IGBT is powered; VFD fault reported | 300 | PLANNED. Scope only: EEII 1 board soldered/tested 9-13 Nov (50 % sig-gen). Needs V/f limits, DRV_FAULT polarity, current-sensor digital format; MCTR 2 spool radius.
2026-11-03 | PC Operator Dashboard | Background-tab heartbeat fix, telemetry source badges, PA MAX in UI, auto mode + obstacle planner | Planned obstacle path runs in the bench model; deadman no longer flaps | 360 | PLANNED. SoW item 5.
2026-11-04 | Pre-Integration Testing | Table 43 stage 4: unpowered full-group signal handshake with PINTEST | handshake.csv: every MCTR 1 / MCTR 2 / EEII 1 / EEII 2 pin checked | 180 | PLANNED. HV off.
2026-11-04 | Meeting - team | Lecture + integration meeting: rail slots, demo order | Rail slots for 5, 6, 9 Nov agreed | 60 | PLANNED.
2026-11-05 | Rail Integration | Rail session 1: PA MAX smoke + sweep at 5-10 m and at the far end, rail SCAN, rail length, lateral motion, encoder vs tape | Smoke PASS at range (< 5 % PER, < 4.15 ms); position error recorded | 300 | PLANNED. ICD Table 43 stage 2. Rail ~20-30 m (MCTR 1 estimate); MCTR 1 proposes 4 or 5 Nov.
2026-11-06 | Rail Integration | Rail session 2: load cell with known masses, brake, magnet on/off + current | Load within 0.1 kg of reference; brake holds; magnet current reported | 300 | PLANNED. With MCTR 2 and EEII 2.
2026-11-07 | Anti-Sway | Measure pendulum period at 3 rope lengths; tune ZV shaper; flat vs shaped sway video | Sway reduced, target < 5 deg | 240 | PLANNED. SoW item 4.
2026-11-08 | Report Writing | Individual report ch 1-2: introduction, SCD, architecture, FFBD, requirements | Draft ch 1-2 | 300 | PLANNED. 2025 example structure.
2026-11-09 | Rail Integration | Rail session 3: E-stop, lost-link mid-move, obstacle-avoidance run; hoist with brake + SPWM on scope | Test log + video per test | 360 | PLANNED. EEII 1 starts final VFD soldering/testing the same day; MCU -> VFD hook-up after their sign-off (12-13 Nov).
2026-11-10 | Verification | Requirement verification matrix; PT1 / PT2 timing from dashboard CSV; report ch 3 | Matrix complete; ch 3 drafted | 360 | PLANNED.
2026-11-11 | Report Writing | Report ch 4 verification; demo dry run with the group; lecture | Dry run passes the demo checklist | 300 | PLANNED.
2026-11-12 | Report Finalisation | MCU -> VFD hook-up and hoisting test with EEII 1; report ch 5-7, final read-through; freeze firmware v5.0 | VFD hoisting logged (or fallback documented); report PDF ready | 300 | PLANNED. Depends on EEII 1 sign-off of their VFD board.
2026-11-13 | Final Demonstration | Final integration, demonstration of the working crane system; submit individual report | Demo done; report submitted | 240 | PLANNED. Due date (integration, demo and report).
2026-11-14 | Group Presentation | REII slides for the group presentation | Slides merged into the group deck | 180 | PLANNED.
2026-11-15 | Portfolio | Compile portfolio: report, timesheet, test logs, CSVs, code | Portfolio pack ready | 180 | PLANNED.
2026-11-16 | Final Presentation | Final group presentation and individual portfolio | Presented; portfolio submitted | 120 | PLANNED. Due date.
TOTALS